# Existing Mili Tasks: Proposed 2027 Plan

Report generation date: 2026-10-12

Source: tasks.csv

# Table of Contents

Update this field in Word to refresh page numbers.

# 1. Executive Summary

The export contains 26 work items: 24 top-level issues and 2 child tasks. All 26 are open; the export contains no closed items. 21 items meet the 24-month staleness definition as of 2026-10-12. Staleness is a triage signal, not evidence that work lacks value.

The recommended 2027 portfolio first strengthens validation and direct-reader testing (#39 with children #60/#61, and #54), then addresses the concrete TFile/restart defect (#41), I/O diagnostics (#28 with #8), recovery design and implementation (#26/#27), and later utility/documentation work (#63, #18, #33). The parts/surfaces initiative (#59) has high strategic value but is program-scale; 2027 should establish a governed design and minimum viable slice before promising ecosystem-wide implementation.

Management decisions required: capacity and ownership are absent from the export; recovery mutation policy is unresolved; public ABI compatibility must be decided for #35; and a cross-tool decision owner is needed for #59. The roadmap is a dependency-based recommendation and must be capacity-validated.

# 2. Data Quality and Methodology

The CSV was parsed with Python's CSV parser so quoted commas and embedded newlines were preserved. Fields analyzed: ID/IID, title, description, type, URL, state, milestone, labels, author, assignee, created/updated/closed/due/start dates, parent fields, estimates, time spent, and weight. Blank values are unknown rather than zero or none.

Encoding: obvious UTF-8-as-Latin-1 mojibake was safely repaired in no fields. No ambiguous text was silently changed.

Priority rubric (recommendation, not objective): user/operational impact 0–20; correctness/reliability/data-loss risk 0–20; explicit GitLab priority 0–15; dependency-unblocking value 0–15; strategic/downstream breadth 0–15; readiness/clarity 0–10; implementation uncertainty adjustment −5 to +5. Age only triggers triage. Child scores inherit the parent portfolio priority and are excluded from totals.

Effort estimates: S = bounded; M = several related code/test changes; L = broad subsystem or cross-tool work; XL = format/program-scale coordination. Stale means last update on or before 2024-10-12. Dispositions distinguish active delivery, discovery, backlog retention, consolidation, and triage.

Limitations: the export has no closed items or discussion threads, mostly blank milestones/dates/estimates, no capacity plan, and sparse acceptance criteria. Source code and linked external issues were not inspected. Schedules, scores, inferred dependencies, effort, risks, and draft criteria are recommendations.

# 3. Backlog Portfolio Overview

| Measure | Count |
| --- | --- |
| All CSV rows | 26 |
| Open | 26 |
| Closed | 0 |
| Top-level issues | 24 |
| Child tasks | 2 |
| Stale rows | 21 |

## Type counts

| Type | Count |
| --- | --- |
| Issue | 24 |
| Task | 2 |

## Top-level stated priority counts

| Stated priority | Count |
| --- | --- |
| High | 3 |
| Low | 6 |
| Medium | 7 |
| Unspecified | 8 |

## Top-level assignee status

| Status | Count |
| --- | --- |
| Assigned | 11 |
| Unassigned | 13 |

## Top-level recommended disposition counts

| Disposition | Count |
| --- | --- |
| Discovery/Design in 2027 | 6 |
| Maintain in Backlog | 1 |
| Merge/Deduplicate | 4 |
| Needs Triage | 3 |
| Schedule for 2027 | 10 |

## Top-level theme counts

| Theme | Count |
| --- | --- |
| Class metadata / slide lines / VisIt integration | 1 |
| Core Mili / dynamic schema | 1 |
| Core Mili / internal architecture | 1 |
| Diagnostic utility / database reading | 1 |
| Documentation / API accuracy | 1 |
| File format / time precision / ecosystem compatibility | 1 |
| File model / labeling / downstream integration | 1 |
| Format documentation | 1 |
| I/O error handling | 2 |
| Metadata grouping / Griz and simulation integration | 1 |
| Metadata model / downstream integration | 1 |
| Parts/surfaces information model / ecosystem integration | 1 |
| Provenance / combining | 1 |
| Public symbols / linkage / compatibility | 1 |
| Recovery / state files / Griz integration | 1 |
| Recovery / time files | 1 |
| State-record validation | 1 |
| State-variable validation | 1 |
| TFiles / restart / state writing | 1 |
| Testing / direct Mili reading | 1 |
| Topology / label validation | 1 |
| Variable declaration validation | 1 |
| Xmilics / batch combining | 1 |

Portfolio totals count 24 top-level issues only. Child tasks #60 and #61 are tracked under #39 and are not double-counted.

# 4. Recommended 2027 Roadmap

This is a proposed dependency sequence, not a staffing commitment. Current assignees are shown exactly as exported; Owner TBD means the CSV has no assignee.

| Track | Item | Disposition | Score/conf. | Effort | Current owner | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| Q1 2027 | #35 rename verbosity function | Schedule for 2027 | 76 / High | S | William Tobin | Explicit external context: libyogrt collision in Diablo; no internal dependency stated. |
| Q1 2027 | #39 Add additional checks for variable declaration. | Schedule for 2027 | 84 / High | M | James Durrenberger | Explicit children: #60 and #61. Inferred: consolidate #34 and align documentation #33. |
| Q1 2027 | #54 Add testing for reading data with mili. Outputing the curve file directly bypassing the mili-python | Schedule for 2027 | 78 / High | M | James Durrenberger | Inferred: prerequisite/risk reducer for #2, #26, #27, #32, #41, #59, and #63. |
| Q1 2027 | #60 Check if Mili is enforcing naming for M_NODE and remove it if does. | Schedule for 2027 | 84 / Medium | S | Owner TBD | Explicit child of #39; score inherited from parent and excluded from portfolio totals. |
| Q1 2027 | #61 Do check for if same element and variable are added to different subrecords | Schedule for 2027 | 84 / Medium | M | Owner TBD | Explicit child of #39; inferred overlap with #34 and documentation #33; score excluded from portfolio totals. |
| Q2 2027 | #8 MILI-8 errno info for output | Merge/Deduplicate | 51 / Medium | S | Owner TBD | Inferred: combine with the broader fopen diagnostic work in #28. |
| Q2 2027 | #28 Better error reporting when file open fails | Schedule for 2027 | 63 / High | S | Owner TBD | Inferred: absorb #8 into a consistent I/O diagnostic approach. |
| Q2 2027 | #41 TFile failure | Schedule for 2027 | 88 / High | M | James Durrenberger | Explicit Diablo workflow. Inferred: coordinate state-integrity tests with #27 and reader coverage #54. |
| Q3 2027 | #26 Mili Recovery | Schedule for 2027 | 79 / Medium | L | Owner TBD | Inferred: coordinate recovery policy with #27 and establish test foundations with #54. |
| Q3 2027 | #27 State File Inconsistancy Recovery | Schedule for 2027 | 82 / Medium | XL | Owner TBD | Inferred: shared recovery design with #26; test support from #54; possible relation to state/restart behavior in #41. |
| Q4 2027 | #18 Review Mili manual | Schedule for 2027 | 57 / Medium | M | Owner TBD | Inferred: complete after planned API-facing changes such as #28, #33, #35, and #39. |
| Q4 2027 | #33 Update Mili Format Doc to specify two svars can't exist in the same srec for the same class/label. | Schedule for 2027 | 52 / Medium | S | William Tobin, James Durrenberger | Inferred: align with #34, #39, and child #61 before publishing. |
| Q4 2027 | #63 Fix the mili dump code. | Schedule for 2027 | 70 / High | L | James Durrenberger | Inferred: direct-reader fixtures from #54 can support validation and expected output. |
| Discovery/Design track | #5 MILI-11 Add Labeling ability to all Mili types | Merge/Deduplicate | 68 / Medium | L | Owner TBD | Inferred: overlaps strongly with #59 and relates to #9, #30, #38, and #42. |
| Discovery/Design track | #9 MILI-7 Find a way to replace the one offs that are being used for simulations | Discovery/Design in 2027 | 55 / Low | L | Owner TBD | Inferred: related to #5, #38, #42, and especially #59. |
| Discovery/Design track | #13 Xmilics wait and combining issues in batch | Discovery/Design in 2027 | 72 / Medium | M | James Durrenberger, Ryan Hathaway | No explicit CSV dependency. Inferred: Xmilics validation may benefit from #54-style direct-reader tests. |
| Discovery/Design track | #15 Provide Mechanism to assign partitions to elements | Discovery/Design in 2027 | 49 / Low | M | Owner TBD | Inferred: coordinate with #59 metadata design and Xmilics ownership. |
| Discovery/Design track | #32 Increased Time Precision | Discovery/Design in 2027 | 69 / Medium | XL | William Tobin, James Durrenberger | Explicit: related Diablo issue 482. Inferred: must coordinate with all readers and format documentation. |
| Discovery/Design track | #38 Arbitrary Groupings | Merge/Deduplicate | 60 / Low | L | Owner TBD | Inferred: make this a use case under #59; also related to #5, #9, and #42. |
| Discovery/Design track | #42 Update classes to provide more information for slide lines | Discovery/Design in 2027 | 64 / Medium | M | James Durrenberger | Explicit external context: VisIt issue 17944. Inferred: evaluate as a #59 grouping use case. |
| Discovery/Design track | #59 Add parts, surfaces into mili. | Discovery/Design in 2027 | 86 / High | XL | Owner TBD | Inferred: umbrella for #5, #9, #38, and #42; may interact with #15 and #30. |
| Deferred backlog | #2 Cleanup Mili_family struct in mili_internal.h | Needs Triage | 48 / Low | L | Owner TBD | Inferred: #54 reader tests should precede a broad refactor. |
| Deferred backlog | #7 MILI-14 Allow addition of new svars/subrecs/mesh topology more dynamically | Maintain in Backlog | 27 / Low | XL | Owner TBD | Inferred: could depend on file-model decisions from #59 and testing from #54. |
| Deferred backlog | #30 Mili Label Conflict Detection | Needs Triage | 58 / Low | M | William Tobin | Inferred: align label rules with #5 and validation framework in #39. |
| Deferred backlog | #34 Add Option To Check if an Entity has the same svar defined for it more than once. | Merge/Deduplicate | 56 / Low | M | William Tobin | Inferred: fold into #39; child #61 covers a closely related cross-subrecord case; coordinate with #33. |
| Deferred backlog | #36 Enforce monotonically increasing MO_ids in an srec | Needs Triage | 50 / Low | S | Owner TBD | Inferred: could share the validation framework and tests of #39. |

Proposed sequencing: Q1 establishes validation and independent reader tests and resolves the small symbol collision. Q2 uses that base for TFile/restart and consistent I/O diagnostics. Q3 treats recovery as a coordinated safety program. Q4 completes dump-tool work and publishes documentation after behavior stabilizes. Discovery runs in parallel only as capacity permits.

# 5. Detailed Issue Analysis

## #2 — Cleanup Mili_family struct in mili_internal.h

GitLab: Cleanup Mili_family struct in mili_internal.h — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/2

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels discussion, enhancement; created 2021-11-23 15:17:38 UTC; updated 2023-09-11 13:42:48 UTC. |
| Ownership | Current assignee Owner TBD; author James Durrenberger (jdurren). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Core Mili / internal architecture |
| Evidence-based summary | Reduce redundancies and clarify responsibilities in the long-lived Mili_family internal structure. |
| Acceptance criteria | Proposed: inventory every field and use site; classify ownership and lifetime; remove or consolidate only fields proven redundant; retain public behavior; add regression coverage for affected family lifecycle paths. |
| Priority | Stated Unspecified; recommended 48/100, confidence Low. Planning recommendation. |
| Estimated effort | L — Broad internal structure change with unknown coupling. |
| Disposition / track | Needs Triage / Deferred backlog |
| Dependencies/relationships | Inferred: #54 reader tests should precede a broad refactor. |
| Risk | Proposed risk: hidden coupling, lifecycle regressions, and ABI risk if the internal type leaks across boundaries. |
| Open triage question | Which redundancies are confirmed, and is Mili_family used outside the library despite being in an internal header? |

## #5 — MILI-11 Add Labeling ability to all Mili types

GitLab: MILI-11 Add Labeling ability to all Mili types — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/5

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels New Feature, Priority::High; created 2021-11-24 08:52:43 UTC; updated 2022-05-02 10:43:25 UTC. |
| Ownership | Current assignee Owner TBD; author Ryan Hathaway (rhathaw). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | File model / labeling / downstream integration |
| Evidence-based summary | Add numeric and string labels across Mili object types to support distinct element-set, material, and part identifiers. |
| Acceptance criteria | Proposed: define label semantics and compatibility; implement at least numeric labels as the stated initial scope; round-trip labels through Mili; demonstrate consumption by the named simulation/post-processing path. |
| Priority | Stated High; recommended 68/100, confidence Medium. Planning recommendation. |
| Estimated effort | L — Cross-format and downstream integration work; initial numeric scope may reduce lift. |
| Disposition / track | Merge/Deduplicate / Discovery/Design track |
| Dependencies/relationships | Inferred: overlaps strongly with #59 and relates to #9, #30, #38, and #42. |
| Risk | Proposed risk: file-format/API compatibility and inconsistent semantics across producers and readers. |
| Open triage question | Should #5 become the labeling workstream under #59, and is numeric-only still an acceptable first release? |

## #7 — MILI-14 Allow addition of new svars/subrecs/mesh topology more dynamically

GitLab: MILI-14 Allow addition of new svars/subrecs/mesh topology more dynamically — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/7

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels New Feature, Priority::Low; created 2021-11-24 08:59:48 UTC; updated 2021-11-24 08:59:48 UTC. |
| Ownership | Current assignee Owner TBD; author Ryan Hathaway (rhathaw). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Core Mili / dynamic schema |
| Evidence-based summary | Explore adding state variables, subrecords, and mesh topology more dynamically. |
| Acceptance criteria | Proposed: document concrete use cases; define allowed lifecycle transitions; specify file-format/API constraints; prototype the smallest compatible change before implementation commitment. |
| Priority | Stated Low; recommended 27/100, confidence Low. Planning recommendation. |
| Estimated effort | XL — The issue explicitly calls this substantial, long-term work and supplies no detailed requirements. |
| Disposition / track | Maintain in Backlog / Deferred backlog |
| Dependencies/relationships | Inferred: could depend on file-model decisions from #59 and testing from #54. |
| Risk | Proposed risk: major format, state-management, compatibility, and downstream-reader complexity. |
| Open triage question | What current workflow is blocked, and which dynamic operation is the minimum useful scope? |

## #8 — MILI-8 errno info for output

GitLab: MILI-8 errno info for output — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/8

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Priority::Low, enhancement; created 2021-11-24 09:01:16 UTC; updated 2021-11-24 09:01:16 UTC. |
| Ownership | Current assignee Owner TBD; author Ryan Hathaway (rhathaw). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | I/O error handling |
| Evidence-based summary | Return useful filesystem error information when fflush fails. |
| Acceptance criteria | Proposed: preserve errno immediately after failure; expose a stable diagnostic through the existing error mechanism; test representative write/flush failures without changing successful behavior. |
| Priority | Stated Low; recommended 51/100, confidence Medium. Planning recommendation. |
| Estimated effort | S — Narrow diagnostic change, subject to public error-interface review. |
| Disposition / track | Merge/Deduplicate / Q2 2027 |
| Dependencies/relationships | Inferred: combine with the broader fopen diagnostic work in #28. |
| Risk | Proposed risk: errno can be overwritten; API/ABI changes are unnecessary if existing diagnostics can carry the message. |
| Open triage question | Should #8 and #28 become one consistent file-I/O diagnostics task? |

## #9 — MILI-7 Find a way to replace the one offs that are being used for simulations

GitLab: MILI-7 Find a way to replace the one offs that are being used for simulations — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/9

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Priority::Low, enhancement; created 2021-11-24 09:02:56 UTC; updated 2022-09-29 07:44:28 UTC. |
| Ownership | Current assignee Owner TBD; author Ryan Hathaway (rhathaw). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Metadata model / downstream integration |
| Evidence-based summary | Inventory one-off simulation parameters such as IntLabel_es_1 and replace them with a coherent Mili capability. |
| Acceptance criteria | Proposed: inventory one-offs and consumers; group use cases; define a compatible general representation; migrate one pilot producer/consumer pair; document fallback handling. |
| Priority | Stated Low; recommended 55/100, confidence Low. Planning recommendation. |
| Estimated effort | L — The discovery inventory and cross-code migrations are not bounded. |
| Disposition / track | Discovery/Design in 2027 / Discovery/Design track |
| Dependencies/relationships | Inferred: related to #5, #38, #42, and especially #59. |
| Risk | Proposed risk: undocumented consumers and incompatible metadata interpretations across simulation codes and Griz. |
| Open triage question | Which one-off parameters remain active, and which producer/consumer pair should be the pilot? |

## #13 — Xmilics wait and combining issues in batch

GitLab: Xmilics wait and combining issues in batch — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/13

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Priority::High, Xmilics, bug; created 2022-02-09 10:25:26 UTC; updated 2022-05-09 08:40:40 UTC. |
| Ownership | Current assignee James Durrenberger, Ryan Hathaway; author James Durrenberger (jdurren). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due 2022-02-11; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Xmilics / batch combining |
| Evidence-based summary | Clarify and correct -wait/-restart behavior so centralized smart-batch use is reliable and does not require flavor-specific wrappers. |
| Acceptance criteria | Explicit/proposed: verify no adverse effect after a run has already finished; characterize unknown flag interactions; reproduce smart-batch polling plus '-wait 30 -restart'; define one centralized invocation; add batch/restart regression cases. |
| Priority | Stated High; recommended 72/100, confidence Medium. Planning recommendation. |
| Estimated effort | M — Concrete operational scenario exists, but expected semantics remain partly undefined. |
| Disposition / track | Discovery/Design in 2027 / Discovery/Design track |
| Dependencies/relationships | No explicit CSV dependency. Inferred: Xmilics validation may benefit from #54-style direct-reader tests. |
| Risk | Proposed risk: hangs, redundant waiting, append/restart corruption, or changed production batch behavior. |
| Open triage question | Are the described smart-batch workflows still active, and what exact behavior is expected for every wait/restart state? |

## #15 — Provide Mechanism to assign partitions to elements

GitLab: Provide Mechanism to assign partitions to elements — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/15

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels New Feature; created 2022-03-18 10:48:06 UTC; updated 2022-03-18 10:48:06 UTC. |
| Ownership | Current assignee Owner TBD; author James Durrenberger (jdurren). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Provenance / combining |
| Evidence-based summary | Persist an element's original simulation partition so users can locate its pre-combine plot file. |
| Acceptance criteria | Proposed: define partition identifier semantics; store and round-trip provenance through combine; expose a query; verify correctness on a multi-partition case. |
| Priority | Stated Unspecified; recommended 49/100, confidence Low. Planning recommendation. |
| Estimated effort | M — Likely touches producer, combiner, storage, and query paths; representation is unspecified. |
| Disposition / track | Discovery/Design in 2027 / Discovery/Design track |
| Dependencies/relationships | Inferred: coordinate with #59 metadata design and Xmilics ownership. |
| Risk | Proposed risk: increased storage, identifier ambiguity after recombination, and downstream compatibility. |
| Open triage question | Is partition provenance still requested, and where should it be stored and queried? |

## #18 — Review Mili manual

GitLab: Review Mili manual — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/18

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Priority::Low, Task, documentation; created 2022-04-14 14:45:04 UTC; updated 2022-04-14 14:45:04 UTC. |
| Ownership | Current assignee Owner TBD; author Ryan Hathaway (rhathaw). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Documentation / API accuracy |
| Evidence-based summary | Reconcile Mili manual function documentation with the implemented interfaces. |
| Acceptance criteria | Proposed: generate an API inventory; compare every documented signature and behavior with authoritative headers/code; correct discrepancies; record the reviewed version; add a documentation check where feasible. |
| Priority | Stated Low; recommended 57/100, confidence Medium. Planning recommendation. |
| Estimated effort | M — Repository-wide documentation audit, but no file-format implementation is implied. |
| Disposition / track | Schedule for 2027 / Q4 2027 |
| Dependencies/relationships | Inferred: complete after planned API-facing changes such as #28, #33, #35, and #39. |
| Risk | Proposed risk: publishing stale signatures or overlooking Fortran/C calling-convention differences. |
| Open triage question | Which manual/version is authoritative, and should generated API references be introduced? |

## #26 — Mili Recovery

GitLab: Mili Recovery — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/26

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Mili, New Feature, Priority::Medium, enhancement; created 2022-06-08 10:41:40 UTC; updated 2022-06-08 10:41:40 UTC. |
| Ownership | Current assignee Owner TBD; author James Durrenberger (jdurren). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Recovery / time files |
| Evidence-based summary | Validate a new time file and rebuild it when corruption or inconsistency is detected. |
| Acceptance criteria | Proposed: specify valid time-file invariants; detect representative damage; rebuild without altering valid data; report recovery actions; test recoverable and unrecoverable cases. |
| Priority | Stated Medium; recommended 79/100, confidence Medium. Planning recommendation. |
| Estimated effort | L — Recovery needs format expertise, failure injection, and strong regression testing. |
| Disposition / track | Schedule for 2027 / Q3 2027 |
| Dependencies/relationships | Inferred: coordinate recovery policy with #27 and establish test foundations with #54. |
| Risk | Proposed risk: silent data loss, false repair, incompatibility with older databases, and insufficient crash fixtures. |
| Open triage question | What corruption cases are recoverable, and must repair be automatic, opt-in, or dry-run first? |

## #27 — State File Inconsistancy Recovery

GitLab: State File Inconsistancy Recovery — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/27

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Mili, New Feature, Priority::Medium, Task, enhancement; created 2022-06-08 10:48:14 UTC; updated 2022-06-08 10:48:14 UTC. |
| Ownership | Current assignee Owner TBD; author James Durrenberger (jdurren). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Recovery / state files / Griz integration |
| Evidence-based summary | Detect corrupted state files, recover to the last successful write, and define policy for partitions with unequal state counts. |
| Acceptance criteria | Proposed: define a valid-state boundary; detect/truncate only with explicit policy; preserve backups or dry-run information; specify least-state versus last-value visualization behavior; validate with Griz stakeholders. |
| Priority | Stated Medium; recommended 82/100, confidence Medium. Planning recommendation. |
| Estimated effort | XL — Data-repair logic plus a cross-product policy decision involving Griz. |
| Disposition / track | Schedule for 2027 / Q3 2027 |
| Dependencies/relationships | Inferred: shared recovery design with #26; test support from #54; possible relation to state/restart behavior in #41. |
| Risk | Proposed risk: irreversible truncation, inconsistent visualization, partial-state exposure, and format-version variation. |
| Open triage question | Who owns the unequal-state policy, and is recovery allowed to mutate original files? |

## #28 — Better error reporting when file open fails

GitLab: Better error reporting when file open fails — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/28

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Mili, Priority::Medium, suggestion; created 2022-08-11 12:16:03 UTC; updated 2022-08-11 12:16:03 UTC. |
| Ownership | Current assignee Owner TBD; author James Durrenberger (jdurren). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | I/O error handling |
| Evidence-based summary | Capture errno and strerror details when fopen fails. |
| Acceptance criteria | Proposed: preserve errno at failure; expose filename, operation, error number, and message through existing diagnostics; test missing, permission-denied, and resource-error paths where portable. |
| Priority | Stated Medium; recommended 63/100, confidence High. Planning recommendation. |
| Estimated effort | S — Narrow, well-described change with modest tests. |
| Disposition / track | Schedule for 2027 / Q2 2027 |
| Dependencies/relationships | Inferred: absorb #8 into a consistent I/O diagnostic approach. |
| Risk | Proposed risk: thread-safety or stale errno if capture is delayed; leaking sensitive paths in messages. |
| Open triage question | Which public error-reporting channel should carry the additional detail? |

## #30 — Mili Label Conflict Detection

GitLab: Mili Label Conflict Detection — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/30

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels None listed; created 2022-09-30 10:20:45 UTC; updated 2022-10-03 09:20:50 UTC. |
| Ownership | Current assignee William Tobin; author William Tobin (tobin6). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Topology / label validation |
| Evidence-based summary | Detect label conflicts while topology is defined incrementally. |
| Acceptance criteria | Proposed: define a conflict; reject or report it deterministically; preserve valid incremental topology; test duplicate and nonconflicting additions. |
| Priority | Stated Unspecified; recommended 58/100, confidence Low. Planning recommendation. |
| Estimated effort | M — Validation change appears bounded, but label semantics and failure behavior are absent. |
| Disposition / track | Needs Triage / Deferred backlog |
| Dependencies/relationships | Inferred: align label rules with #5 and validation framework in #39. |
| Risk | Proposed risk: rejecting formerly accepted files or detecting conflicts too late. |
| Open triage question | What constitutes a label conflict, at what scope, and should it be an error or warning? |

## #32 — Increased Time Precision

GitLab: Increased Time Precision — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/32

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels discussion; created 2022-10-04 17:23:51 UTC; updated 2022-10-05 13:55:04 UTC. |
| Ownership | Current assignee William Tobin, James Durrenberger; author William Tobin (tobin6). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | File format / time precision / ecosystem compatibility |
| Evidence-based summary | Assess higher-precision time storage, including a file-version change and updates to Mili, mili-python, and external producers/consumers. |
| Acceptance criteria | Proposed: quantify required precision; design versioned on-disk representation; define old/new read-write compatibility and conversion; inventory consumers; prototype round-trip and numerical tests. |
| Priority | Stated Unspecified; recommended 69/100, confidence Medium. Planning recommendation. |
| Estimated effort | XL — The issue itself identifies ecosystem-wide format and reader changes. |
| Disposition / track | Discovery/Design in 2027 / Discovery/Design track |
| Dependencies/relationships | Explicit: related Diablo issue 482. Inferred: must coordinate with all readers and format documentation. |
| Risk | Proposed risk: format fragmentation, precision conversion changes, larger files, and external-code incompatibility. |
| Open triage question | What precision/range is required, and must new libraries read/write old and new versions bidirectionally? |

## #33 — Update Mili Format Doc to specify two svars can't exist in the same srec for the same class/label.

GitLab: Update Mili Format Doc to specify two svars can't exist in the same srec for the same class/label. — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/33

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels None listed; created 2022-10-05 09:40:32 UTC; updated 2022-10-05 14:48:13 UTC. |
| Ownership | Current assignee William Tobin, James Durrenberger; author William Tobin (tobin6). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Format documentation |
| Evidence-based summary | Document that two state variables cannot coexist in one state record for the same class/label. |
| Acceptance criteria | Proposed: confirm the invariant in code/tests; add normative wording and an invalid example to the format documentation; cross-link validation behavior. |
| Priority | Stated Unspecified; recommended 52/100, confidence Medium. Planning recommendation. |
| Estimated effort | S — Small documentation change, though the blank description requires invariant confirmation. |
| Disposition / track | Schedule for 2027 / Q4 2027 |
| Dependencies/relationships | Inferred: align with #34, #39, and child #61 before publishing. |
| Risk | Proposed risk: documenting behavior that is not consistently enforced. |
| Open triage question | Is this an existing format invariant or a desired new restriction? |

## #34 — Add Option To Check if an Entity has the same svar defined for it more than once.

GitLab: Add Option To Check if an Entity has the same svar defined for it more than once. — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/34

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels None listed; created 2022-10-05 09:48:00 UTC; updated 2022-10-05 09:48:00 UTC. |
| Ownership | Current assignee William Tobin; author William Tobin (tobin6). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | State-variable validation |
| Evidence-based summary | Offer a user-controlled check for the same state variable being defined more than once for an entity. |
| Acceptance criteria | Proposed: define duplicate scope; decide default and compatibility; expose the option; produce actionable diagnostics; test enabled/disabled behavior. |
| Priority | Stated Unspecified; recommended 56/100, confidence Low. Planning recommendation. |
| Estimated effort | M — Small description leaves API and duplicate semantics unresolved. |
| Disposition / track | Merge/Deduplicate / Deferred backlog |
| Dependencies/relationships | Inferred: fold into #39; child #61 covers a closely related cross-subrecord case; coordinate with #33. |
| Risk | Proposed risk: behavior divergence when optional and compatibility regressions when enabled by default. |
| Open triage question | Is this fully covered by #39/#61, and why must the check be optional? |

## #35 — rename verbosity function

GitLab: rename verbosity function — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/35

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Priority::Medium, cleanup; created 2022-10-28 10:28:57 UTC; updated 2022-10-28 10:28:57 UTC. |
| Ownership | Current assignee William Tobin; author William Tobin (tobin6). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Public symbols / linkage / compatibility |
| Evidence-based summary | Avoid a link-time collision with libyogrt by renaming the generic verbosity symbol to mili_verbosity. |
| Acceptance criteria | Proposed: reproduce or verify the collision; introduce mili_verbosity; preserve the old public symbol through a compatibility strategy if ABI requires it; test linking with affected libyogrt configurations. |
| Priority | Stated Medium; recommended 76/100, confidence High. Planning recommendation. |
| Estimated effort | S — Specific symbol conflict and target name are supplied; compatibility requires care. |
| Disposition / track | Schedule for 2027 / Q1 2027 |
| Dependencies/relationships | Explicit external context: libyogrt collision in Diablo; no internal dependency stated. |
| Risk | Proposed risk: breaking C/Fortran callers or shared-library ABI by removing the old symbol. |
| Open triage question | Is verbosity public ABI, and what deprecation window is required for the old symbol? |

## #36 — Enforce monotonically increasing MO_ids in an srec

GitLab: Enforce monotonically increasing MO_ids in an srec — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/36

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels None listed; created 2022-11-01 10:02:21 UTC; updated 2022-11-01 10:06:01 UTC. |
| Ownership | Current assignee Owner TBD; author William Tobin (tobin6). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | State-record validation |
| Evidence-based summary | Enforce monotonically increasing MO_ids within a state record. |
| Acceptance criteria | Proposed: define strict versus non-strict ordering and scope; validate at the appropriate boundary; issue a clear error; test ordered, duplicate, and descending identifiers. |
| Priority | Stated Unspecified; recommended 50/100, confidence Low. Planning recommendation. |
| Estimated effort | S — Likely a bounded check, but the empty description leaves semantics uncertain. |
| Disposition / track | Needs Triage / Deferred backlog |
| Dependencies/relationships | Inferred: could share the validation framework and tests of #39. |
| Risk | Proposed risk: newly rejecting legacy data that readers currently tolerate. |
| Open triage question | Is monotonicity already a documented format invariant, and must readers accept historical violations? |

## #38 — Arbitrary Groupings

GitLab: Arbitrary Groupings — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/38

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels None listed; created 2022-11-01 11:50:33 UTC; updated 2022-11-01 11:50:33 UTC. |
| Ownership | Current assignee Owner TBD; author William Tobin (tobin6). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Metadata grouping / Griz and simulation integration |
| Evidence-based summary | Represent named arbitrary groups of topological entities to organize boundary-condition/contact output without Griz hard-coding. |
| Acceptance criteria | Proposed: validate user workflows; decide application/TI parameter versus core-format representation; define same/mixed-type rules; prototype producer and Griz/mili-python consumption. |
| Priority | Stated Unspecified; recommended 60/100, confidence Low. Planning recommendation. |
| Estimated effort | L — Cross-tool design is required even if core Mili changes prove unnecessary. |
| Disposition / track | Merge/Deduplicate / Discovery/Design track |
| Dependencies/relationships | Inferred: make this a use case under #59; also related to #5, #9, and #42. |
| Risk | Proposed risk: overlapping grouping concepts and inconsistent producer/consumer implementations. |
| Open triage question | Does #59's parts/surfaces model subsume arbitrary groups, or is a separate generic concept required? |

## #39 — Add additional checks for variable declaration.

GitLab: Add additional checks for variable declaration. — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/39

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Mili, Priority::High, enhancement; created 2022-11-10 10:10:10 UTC; updated 2024-11-06 13:33:41 UTC. |
| Ownership | Current assignee James Durrenberger; author James Durrenberger (jdurren). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | No under the 24-month rule. |
| Area | Variable declaration validation |
| Evidence-based summary | Extend declaration checks beyond scalar redeclarations and coordinate related naming and cross-subrecord checks. |
| Acceptance criteria | Proposed: enumerate legal/illegal redeclarations by variable type; implement deterministic diagnostics; complete child investigations #60 and #61; add positive and negative regression tests. |
| Priority | Stated High; recommended 84/100, confidence High. Planning recommendation. |
| Estimated effort | M — High-priority parent has two concrete children and a bounded validation theme. |
| Disposition / track | Schedule for 2027 / Q1 2027 |
| Dependencies/relationships | Explicit children: #60 and #61. Inferred: consolidate #34 and align documentation #33. |
| Risk | Proposed risk: rejecting legacy definitions, inconsistent checks by variable type, and unclear error timing. |
| Open triage question | What compatibility policy applies to previously accepted redeclarations? |

## #41 — TFile failure

GitLab: TFile failure — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/41

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Mili, Priority::Medium, bug; created 2023-04-12 12:53:46 UTC; updated 2023-09-05 09:08:49 UTC. |
| Ownership | Current assignee James Durrenberger; author William Tobin (tobin6). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | TFiles / restart / state writing |
| Evidence-based summary | Make TFiles work when an underfull reference state is intentionally rewritten through mf_restart_at_state. |
| Acceptance criteria | Proposed: reproduce the described zero-length TFile path; define supported underfull-state semantics; retain enough state information for restart; test TFiles on/off and successful/failed rewrite paths. |
| Priority | Stated Medium; recommended 88/100, confidence High. Planning recommendation. |
| Estimated effort | M — Detailed reproducer and failure mechanism exist, but desired error semantics need confirmation. |
| Disposition / track | Schedule for 2027 / Q2 2027 |
| Dependencies/relationships | Explicit Diablo workflow. Inferred: coordinate state-integrity tests with #27 and reader coverage #54. |
| Risk | Proposed risk: state corruption, truncate failure, changed mf_end_state behavior, or masking an invalid state. |
| Open triage question | Should the underfull-state error remain, and what durable TFile state must exist after it? |

## #42 — Update classes to provide more information for slide lines

GitLab: Update classes to provide more information for slide lines — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/42

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels New Feature, Priority::Medium, Task, discussion; created 2023-05-05 07:15:31 UTC; updated 2023-05-08 09:00:51 UTC. |
| Ownership | Current assignee James Durrenberger; author James Durrenberger (jdurren). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Class metadata / slide lines / VisIt integration |
| Evidence-based summary | Represent slide-line classes distinctly from ordinary materials so user interfaces can group them correctly. |
| Acceptance criteria | Proposed: define the class metadata; write/read it compatibly; demonstrate grouping in the named VisIt interaction; document behavior for older databases. |
| Priority | Stated Medium; recommended 64/100, confidence Medium. Planning recommendation. |
| Estimated effort | M — Cross-tool feature with a clear UI need but unspecified representation. |
| Disposition / track | Discovery/Design in 2027 / Discovery/Design track |
| Dependencies/relationships | Explicit external context: VisIt issue 17944. Inferred: evaluate as a #59 grouping use case. |
| Risk | Proposed risk: adding another special case instead of a general model; downstream-reader divergence. |
| Open triage question | Can the #59 parts/surfaces structure represent slide lines without a dedicated special case? |

## #54 — Add testing for reading data with mili.  Outputing the curve file directly bypassing the mili-python

GitLab: Add testing for reading data with mili.  Outputing the curve file directly bypassing the mili-python — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/54

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Mili, Priority::Low; created 2024-06-05 11:34:36 UTC; updated 2024-06-05 11:34:36 UTC. |
| Ownership | Current assignee James Durrenberger; author James Durrenberger (jdurren). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | Yes under the 24-month rule. |
| Area | Testing / direct Mili reading |
| Evidence-based summary | Add tests that exercise Mili's own reading path and direct curve output rather than relying only on mili-python. |
| Acceptance criteria | Proposed: identify untested reader APIs; build deterministic fixture databases; read and verify values directly with Mili; emit/compare curve output; retain independent expected results. |
| Priority | Stated Low; recommended 78/100, confidence High. Planning recommendation. |
| Estimated effort | M — Clear coverage gap; fixture and oracle construction create moderate work. |
| Disposition / track | Schedule for 2027 / Q1 2027 |
| Dependencies/relationships | Inferred: prerequisite/risk reducer for #2, #26, #27, #32, #41, #59, and #63. |
| Risk | Proposed risk: circular tests if expected data is generated by the same implementation under test. |
| Open triage question | Which direct reader/curve interfaces and database variants are highest priority? |

## #59 — Add parts, surfaces into mili.

GitLab: Add parts, surfaces into mili. — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/59

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Mili, New Feature, Priority::Medium, Xmilics, enhancement; created 2024-11-01 14:54:17 UTC; updated 2024-11-01 14:54:17 UTC. |
| Ownership | Current assignee Owner TBD; author James Durrenberger (jdurren). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due 2024-12-12; start Unknown; estimate Unknown; spent Unknown; weight 5. |
| Staleness | No under the 24-month rule. |
| Area | Parts/surfaces information model / ecosystem integration |
| Evidence-based summary | Define and implement a clearer parts/surfaces organization spanning analyst input, simulation producers, Mili, Griz, Diablo, and ParaDyn. |
| Acceptance criteria | Explicit checklist: define structure; obtain analyst and simulation input; define post-processing interactions; update Mili; provide data to Griz; update Diablo and ParaDyn output. Proposed: add compatibility/versioning and end-to-end acceptance cases. |
| Priority | Stated Medium; recommended 86/100, confidence High. Planning recommendation. |
| Estimated effort | XL — Eight explicit cross-organization steps and multiple producers/consumers make this a program-scale effort. |
| Disposition / track | Discovery/Design in 2027 / Discovery/Design track |
| Dependencies/relationships | Inferred: umbrella for #5, #9, #38, and #42; may interact with #15 and #30. |
| Risk | Proposed risk: unclear ontology, ecosystem coordination, format/API compatibility, and an implementation scope larger than available capacity. |
| Open triage question | Who is the decision owner for the shared model, and which producer/consumer path defines the minimum viable slice? |

## #60 — Check if Mili is enforcing naming for M_NODE and remove it if does.

GitLab: Check if Mili is enforcing naming for M_NODE and remove it if does. — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/60

| Field | Analysis |
| --- | --- |
| Record | Task; state Open; labels None listed; created 2024-11-06 13:31:13 UTC; updated 2024-11-06 13:31:13 UTC. |
| Ownership | Current assignee Owner TBD; author James Durrenberger (jdurren). |
| Parent | #39 Add additional checks for variable declaration. |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | No under the 24-month rule. |
| Area | Naming validation |
| Evidence-based summary | Investigate whether Mili enforces naming for M_NODE and remove that enforcement if it exists. |
| Acceptance criteria | Proposed: locate and document the rule; determine intended compatibility; test current behavior; remove only the confirmed unwanted restriction; add a regression case. |
| Priority | Stated Unspecified; recommended 84/100, confidence Medium. Child score inherited from #39 and excluded from totals. |
| Estimated effort | S — Focused investigation and possible narrow code change. |
| Disposition / track | Schedule for 2027 / Q1 2027 |
| Dependencies/relationships | Explicit child of #39; score inherited from parent and excluded from portfolio totals. |
| Risk | Proposed risk: relaxing a rule required by a reader or format convention. |
| Open triage question | Which M_NODE names must be accepted, and do downstream consumers assume the current name? |

## #61 — Do check for if same element and variable are added to different subrecords

GitLab: Do check for if same element and variable are added to different subrecords — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/61

| Field | Analysis |
| --- | --- |
| Record | Task; state Open; labels None listed; created 2024-11-06 13:32:15 UTC; updated 2024-11-06 13:32:15 UTC. |
| Ownership | Current assignee Owner TBD; author James Durrenberger (jdurren). |
| Parent | #39 Add additional checks for variable declaration. |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | No under the 24-month rule. |
| Area | Variable/subrecord validation |
| Evidence-based summary | Check whether the same element and variable are assigned across different subrecords. |
| Acceptance criteria | Proposed: define duplicate scope across subrecords; detect the illegal case during declaration; report both conflicting subrecords; test legal and illegal layouts. |
| Priority | Stated Unspecified; recommended 84/100, confidence Medium. Child score inherited from #39 and excluded from totals. |
| Estimated effort | M — Focused child, but entity/variable identity and compatibility semantics need definition. |
| Disposition / track | Schedule for 2027 / Q1 2027 |
| Dependencies/relationships | Explicit child of #39; inferred overlap with #34 and documentation #33; score excluded from portfolio totals. |
| Risk | Proposed risk: rejecting legacy layouts or misidentifying legitimate repeated variables. |
| Open triage question | Is every cross-subrecord repetition illegal, or only repetition for the same class/label/entity? |

## #63 — Fix the mili dump code.

GitLab: Fix the mili dump code. — https://rzlc.llnl.gov/gitlab/mdg/mili/mili/-/work_items/63

| Field | Analysis |
| --- | --- |
| Record | Issue; state Open; labels Priority::Low, Task, cleanup; created 2025-04-07 10:12:08 UTC; updated 2025-04-07 10:43:23 UTC. |
| Ownership | Current assignee James Durrenberger; author James Durrenberger (jdurren). |
| Parent | None (top-level). |
| Planning metadata | Milestone Unknown; due Unknown; start Unknown; estimate Unknown; spent Unknown; weight Unknown. |
| Staleness | No under the 24-month rule. |
| Area | Diagnostic utility / database reading |
| Evidence-based summary | Restore useful mili-dump output by validating databases, replacing fragile low-level access, using higher-level APIs, cleaning formatting, and removing HAVE_EPRINT dependence. |
| Acceptance criteria | Explicit checklist: initial validity check; remove error-prone low-level access; use higher-level structure/value access; clean output; remove HAVE_EPRINT compile requirement. Proposed: add representative golden-output/error tests. |
| Priority | Stated Low; recommended 70/100, confidence High. Planning recommendation. |
| Estimated effort | L — Five concrete cleanup steps across access and presentation paths. |
| Disposition / track | Schedule for 2027 / Q4 2027 |
| Dependencies/relationships | Inferred: direct-reader fixtures from #54 can support validation and expected output. |
| Risk | Proposed risk: loss of low-level diagnostic visibility and output-format compatibility for scripts. |
| Open triage question | Which output modes and formats are compatibility requirements, and what databases form the acceptance suite? |

# 6. Dependency, Overlap, and Consolidation Analysis

• Explicit hierarchy: #60 and #61 are children of #39. No other explicit parent relationship is present in the export.

• Recommended validation cluster (inferred): manage #34 and #36 alongside #39; use #33 to document the confirmed invariant. Do not close or merge until duplicate scope and backward compatibility are confirmed.

• Recommended metadata cluster (inferred): use #59 as the design umbrella and treat #5, #9, #38, and #42 as use cases or workstreams. #15 may share provenance representation but has a distinct outcome.

• Recommended I/O consolidation (inferred): merge #8's fflush diagnostic with #28's fopen diagnostic while retaining both IIDs.

• Recommended recovery program (inferred): coordinate #26 and #27 under one safety policy; use #54 fixtures. #41 is a concrete restart defect and should land before or alongside recovery tests.

• Testing dependency (inferred): #54 reduces risk for #2, #26, #27, #32, #41, #59, and #63.

• Documentation sequencing (inferred): update #18 and #33 after validation, diagnostics, and compatibility decisions stabilize.

# 7. Risk Register

| Risk | Items | Likelihood | Impact | Proposed mitigation | Current owner |
| --- | --- | --- | --- | --- | --- |
| State/data loss during repair | #26, #27 | Medium | Critical | Require invariant specification, dry-run/backup policy, corrupt fixtures, and explicit mutation approval. | Owner TBD |
| Restart/TFile corruption | #41 | High | High | Reproduce exact workflow; test TFiles on/off and underfull-state recovery before release. | James Durrenberger |
| File-format fragmentation | #5, #32, #59 | Medium | High | Version the format deliberately; publish compatibility matrix; test old/new readers and writers. | Owner TBD |
| Public ABI break | #35 | Medium | High | Inventory symbol consumers and provide a compatibility/deprecation path. | William Tobin |
| Legacy data rejected by new checks | #30, #33, #34, #36, #39, #61 | Medium | High | Define invariants and reader/writer policy; add legacy fixtures and diagnostics. | James Durrenberger |
| Circular or weak test oracle | #54 | Medium | High | Use independently known expected values and fixed fixtures rather than the same reader to generate truth. | James Durrenberger |
| Cross-tool design divergence | #5, #9, #38, #42, #59 | High | High | Name a decision owner, agree terminology, and deliver one end-to-end minimum viable slice. | Owner TBD |
| Batch behavior regression | #13 | Medium | High | Capture active production scenarios and automate wait/restart/append state-machine tests. | James Durrenberger, Ryan Hathaway |
| Diagnostic output incompatibility | #28, #63 | Low | Medium | Preserve stable output where required and document/add machine-readable behavior if scripts consume it. | Owner TBD |

# 8. Triage Decisions Needed

• #2: Which redundancies are confirmed, and is Mili_family used outside the library despite being in an internal header? Current assignee: Owner TBD; stale: yes; recommendation: Needs Triage.

• #5: Should #5 become the labeling workstream under #59, and is numeric-only still an acceptable first release? Current assignee: Owner TBD; stale: yes; recommendation: Merge/Deduplicate.

• #7: What current workflow is blocked, and which dynamic operation is the minimum useful scope? Current assignee: Owner TBD; stale: yes; recommendation: Maintain in Backlog.

• #8: Should #8 and #28 become one consistent file-I/O diagnostics task? Current assignee: Owner TBD; stale: yes; recommendation: Merge/Deduplicate.

• #9: Which one-off parameters remain active, and which producer/consumer pair should be the pilot? Current assignee: Owner TBD; stale: yes; recommendation: Discovery/Design in 2027.

• #13: Are the described smart-batch workflows still active, and what exact behavior is expected for every wait/restart state? Current assignee: James Durrenberger, Ryan Hathaway; stale: yes; recommendation: Discovery/Design in 2027.

• #15: Is partition provenance still requested, and where should it be stored and queried? Current assignee: Owner TBD; stale: yes; recommendation: Discovery/Design in 2027.

• #18: Which manual/version is authoritative, and should generated API references be introduced? Current assignee: Owner TBD; stale: yes; recommendation: Schedule for 2027.

• #26: What corruption cases are recoverable, and must repair be automatic, opt-in, or dry-run first? Current assignee: Owner TBD; stale: yes; recommendation: Schedule for 2027.

• #27: Who owns the unequal-state policy, and is recovery allowed to mutate original files? Current assignee: Owner TBD; stale: yes; recommendation: Schedule for 2027.

• #28: Which public error-reporting channel should carry the additional detail? Current assignee: Owner TBD; stale: yes; recommendation: Schedule for 2027.

• #30: What constitutes a label conflict, at what scope, and should it be an error or warning? Current assignee: William Tobin; stale: yes; recommendation: Needs Triage.

• #32: What precision/range is required, and must new libraries read/write old and new versions bidirectionally? Current assignee: William Tobin, James Durrenberger; stale: yes; recommendation: Discovery/Design in 2027.

• #33: Is this an existing format invariant or a desired new restriction? Current assignee: William Tobin, James Durrenberger; stale: yes; recommendation: Schedule for 2027.

• #34: Is this fully covered by #39/#61, and why must the check be optional? Current assignee: William Tobin; stale: yes; recommendation: Merge/Deduplicate.

• #35: Is verbosity public ABI, and what deprecation window is required for the old symbol? Current assignee: William Tobin; stale: yes; recommendation: Schedule for 2027.

• #36: Is monotonicity already a documented format invariant, and must readers accept historical violations? Current assignee: Owner TBD; stale: yes; recommendation: Needs Triage.

• #38: Does #59's parts/surfaces model subsume arbitrary groups, or is a separate generic concept required? Current assignee: Owner TBD; stale: yes; recommendation: Merge/Deduplicate.

• #41: Should the underfull-state error remain, and what durable TFile state must exist after it? Current assignee: James Durrenberger; stale: yes; recommendation: Schedule for 2027.

• #42: Can the #59 parts/surfaces structure represent slide lines without a dedicated special case? Current assignee: James Durrenberger; stale: yes; recommendation: Discovery/Design in 2027.

• #54: Which direct reader/curve interfaces and database variants are highest priority? Current assignee: James Durrenberger; stale: yes; recommendation: Schedule for 2027.

• #59: Who is the decision owner for the shared model, and which producer/consumer path defines the minimum viable slice? Current assignee: Owner TBD; stale: no; recommendation: Discovery/Design in 2027.

• #60: Which M_NODE names must be accepted, and do downstream consumers assume the current name? Current assignee: Owner TBD; stale: no; recommendation: Schedule for 2027.

• #61: Is every cross-subrecord repetition illegal, or only repetition for the same class/label/entity? Current assignee: Owner TBD; stale: no; recommendation: Schedule for 2027.

# 9. Deferred Backlog and Appendix

Deferred implementation does not mean rejection. It means the export does not support an active 2027 commitment before clarification, consolidation, or capacity validation.

| IID | Title | Disposition | Reason/decision needed |
| --- | --- | --- | --- |
| #2 | Cleanup Mili_family struct in mili_internal.h | Needs Triage | Which redundancies are confirmed, and is Mili_family used outside the library despite being in an internal header? |
| #7 | MILI-14 Allow addition of new svars/subrecs/mesh topology more dynamically | Maintain in Backlog | What current workflow is blocked, and which dynamic operation is the minimum useful scope? |
| #30 | Mili Label Conflict Detection | Needs Triage | What constitutes a label conflict, at what scope, and should it be an error or warning? |
| #34 | Add Option To Check if an Entity has the same svar defined for it more than once. | Merge/Deduplicate | Is this fully covered by #39/#61, and why must the check be optional? |
| #36 | Enforce monotonically increasing MO_ids in an srec | Needs Triage | Is monotonicity already a documented format invariant, and must readers accept historical violations? |

## Appendix A — Full Reconciled Inventory

| IID | Type | State | Parent | GitLab priority | Score | Confidence | Effort | Disposition | Track |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Issue | Open | — | Unspecified | 48 | Low | L | Needs Triage | Deferred backlog |
| 5 | Issue | Open | — | High | 68 | Medium | L | Merge/Deduplicate | Discovery/Design track |
| 7 | Issue | Open | — | Low | 27 | Low | XL | Maintain in Backlog | Deferred backlog |
| 8 | Issue | Open | — | Low | 51 | Medium | S | Merge/Deduplicate | Q2 2027 |
| 9 | Issue | Open | — | Low | 55 | Low | L | Discovery/Design in 2027 | Discovery/Design track |
| 13 | Issue | Open | — | High | 72 | Medium | M | Discovery/Design in 2027 | Discovery/Design track |
| 15 | Issue | Open | — | Unspecified | 49 | Low | M | Discovery/Design in 2027 | Discovery/Design track |
| 18 | Issue | Open | — | Low | 57 | Medium | M | Schedule for 2027 | Q4 2027 |
| 26 | Issue | Open | — | Medium | 79 | Medium | L | Schedule for 2027 | Q3 2027 |
| 27 | Issue | Open | — | Medium | 82 | Medium | XL | Schedule for 2027 | Q3 2027 |
| 28 | Issue | Open | — | Medium | 63 | High | S | Schedule for 2027 | Q2 2027 |
| 30 | Issue | Open | — | Unspecified | 58 | Low | M | Needs Triage | Deferred backlog |
| 32 | Issue | Open | — | Unspecified | 69 | Medium | XL | Discovery/Design in 2027 | Discovery/Design track |
| 33 | Issue | Open | — | Unspecified | 52 | Medium | S | Schedule for 2027 | Q4 2027 |
| 34 | Issue | Open | — | Unspecified | 56 | Low | M | Merge/Deduplicate | Deferred backlog |
| 35 | Issue | Open | — | Medium | 76 | High | S | Schedule for 2027 | Q1 2027 |
| 36 | Issue | Open | — | Unspecified | 50 | Low | S | Needs Triage | Deferred backlog |
| 38 | Issue | Open | — | Unspecified | 60 | Low | L | Merge/Deduplicate | Discovery/Design track |
| 39 | Issue | Open | — | High | 84 | High | M | Schedule for 2027 | Q1 2027 |
| 41 | Issue | Open | — | Medium | 88 | High | M | Schedule for 2027 | Q2 2027 |
| 42 | Issue | Open | — | Medium | 64 | Medium | M | Discovery/Design in 2027 | Discovery/Design track |
| 54 | Issue | Open | — | Low | 78 | High | M | Schedule for 2027 | Q1 2027 |
| 59 | Issue | Open | — | Medium | 86 | High | XL | Discovery/Design in 2027 | Discovery/Design track |
| 60 | Task | Open | 39 | Unspecified | 84 | Medium | S | Schedule for 2027 | Q1 2027 |
| 61 | Task | Open | 39 | Unspecified | 84 | Medium | M | Schedule for 2027 | Q1 2027 |
| 63 | Issue | Open | — | Low | 70 | High | L | Schedule for 2027 | Q4 2027 |

Reconciliation: 26 inventory rows = 24 top-level issues + 2 child tasks. Open: 26; closed: 0.

## Appendix B — Validation Record

• Parsed CSV rows: 26; analyzed rows: 26; reconciled: yes.

• Open items represented in detailed analysis: 26 of 26.

• Top-level portfolio count: 24; child tasks excluded from portfolio totals: 2.

• Every cited issue URL was taken directly from tasks.csv.

• Proposed priorities, effort, schedule, dependencies, criteria, risks, and dispositions are labeled as recommendations, estimates, proposed, or inferred.

• The DOCX package and UTF-8 text encoding are validated after generation.